## Project Parameters
[Company Name]
Event Management Project Tracker
Company Confidential
Shaded cells are calculated for you. You do not need to enter anything into them.
Project type | Account manager | Project manager | Strategy specialist | Design specialist | Event staff | Administration staff | Total
Event strategy development | 20% | 10% | 60% | 0% | 0% | 10% | 100%
Event planning | 20% | 50% | 10% | 10% | 0% | 10% | 100%
Event design | 20% | 20% | 0% | 50% | 0% | 10% | 100%
Event logistics | 20% | 60% | 0% | 0% | 10% | 10% | 100%
Event staffing | 20% | 10% | 0% | 0% | 60% | 10% | 100%
Event assessment | 20% | 20% | 20% | 20% | 0% | 20% | 100%
Blended rates | 180 | 120 | 150 | 100 | 80 | 60

## Planning
[Company Name]
Event Management Project Tracker
Company Confidential
Project name | Project type | Estimated start | Estimated finish | Estimated work | Duration
A. Datum Corporation | Event strategy development | 2005-01-04 | 2005-03-04 | 200 | 60
Adventure Works | Event planning | 2005-01-20 | 2005-02-21 | 400 | 31
Alpine Ski House | Event design | 2005-02-06 | 2005-04-16 | 500 | 70
Baldwin Museum of Science | Event logistics | 2005-02-24 | 2005-04-25 | 150 | 61
Blue Yonder Airlines | Event staffing | 2005-03-08 | 2005-03-18 | 250 | 10
City Power & Light | Event assessment | 2005-03-19 | 2005-04-29 | 300 | 40
Coho Vineyard | Event planning | 2005-04-10 | 2005-04-20 | 500 | 10
Coho Winery | Event logistics | 2005-04-18 | 2005-05-12 | 750 | 24
Coho Vineyard & Winery | Event assessment | 2005-05-12 | 2005-06-22 | 450 | 40
Contoso, Ltd. | Event staffing | 2005-05-23 | 2005-07-21 | 250 | 58
Contoso Pharmaceuticals | Event planning | 2005-06-14 | 2005-08-12 | 200 | 58
Consolidated Messenger | Event strategy development | 2005-06-30 | 2005-08-30 | 180 | 60
Fabrikam, Inc. | Event staffing | 2005-01-16 | 2005-08-15 | 250 | 209
Fourth Coffee | Event logistics | 2005-07-17 | 2005-09-01 | 240 | 44
Graphic Design Institute | Event design | 2005-07-25 | 2005-09-30 | 320 | 65
Humongous Insurance | Event planning | 2005-08-01 | 2005-10-01 | 550 | 60
Litware, Inc. | Event design | 2005-08-20 | 2005-10-02 | 350 | 42
Lucerne Publishing | Event strategy development | 2005-09-02 | 2005-11-12 | 200 | 70
Margie's Travel | Event planning | 2005-09-12 | 2005-11-25 | 220 | 73
Northwind Traders | Event assessment | 2005-10-12 | 2005-12-20 | 600 | 68
Proseware, Inc. | Event logistics | 2005-10-24 | 2005-12-14 | 525 | 50
School of Fine Art | Event planning | 2005-11-04 | 2005-11-24 | 180 | 20
TOTAL |  |  |  | 7565

## Tracking
[Company Name]
Event Management Project Tracker
Company Confidential
Project name | Actual start | Actual finish | Actual work | Actual duration
A. Datum Corporation | 2005-01-04 | 2005-03-09 | 220 | 65
Adventure Works | 2005-01-25 | 2005-02-28 | 390 | 33
Alpine Ski House | 2005-02-10 | 2005-04-23 | 500 | 73
Baldwin Museum of Science | 2005-02-22 | 2005-04-29 | 145 | 67
Blue Yonder Airlines | 2005-03-09 | 2005-03-28 | 255 | 19
City Power & Light | 2005-03-19 | 2005-05-05 | 310 | 46
Coho Vineyard | 2005-04-12 | 2005-04-27 | 510 | 15
Coho Winery | 2005-04-17 | 2005-05-16 | 790 | 29
Coho Vineyard & Winery | 2005-05-15 | 2005-06-24 | 430 | 39
Contoso, Ltd. | 2005-05-24 | 2005-07-24 | 235 | 60
Contoso Pharmaceuticals | 2005-06-16 | 2005-08-16 | 235 | 60
Consolidated Messenger | 2005-07-02 | 2005-09-25 | 190 | 83
Fabrikam, Inc. | 2005-01-18 | 2005-08-16 | 230 | 208
Fourth Coffee | 2005-07-19 | 2005-09-15 | 225 | 56
Graphic Design Institute | 2005-07-26 | 2005-10-20 | 305 | 84
Humongous Insurance | 2005-08-01 | 2005-10-14 | 565 | 73
Litware, Inc. | 2005-08-28 | 2005-10-21 | 350 | 53
Lucerne Publishing | 2005-09-04 | 2005-11-15 | 205 | 71
Margie's Travel | 2005-09-13 | 2005-11-29 | 230 | 76
Northwind Traders | 2005-10-22 | 2005-12-24 | 560 | 62
Proseware, Inc. | 2005-10-14 | 2005-12-10 | 540 | 56
School of Fine Art | 2005-11-04 | 2005-11-20 | 190 | 16
TOTAL |  |  | 7610

## Planned Totals
[Company Name]
Event Management Project Tracker
Company Confidential
Project name | Account manager | Project manager | Strategy specialist | Design specialist | Event staff | Administration staff | Total
A. Datum Corporation | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 28800
Adventure Works | 14400 | 24000 | 6000 | 4000 | 0 | 2400 | 50800
Alpine Ski House | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 58000
Baldwin Museum of Science | 5400 | 10800 | 0 | 0 | 1200 | 900 | 18300
Blue Yonder Airlines | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 25500
City Power & Light | 10800 | 7200 | 9000 | 6000 | 0 | 3600 | 36600
Coho Vineyard | 18000 | 30000 | 7500 | 5000 | 0 | 3000 | 63500
Coho Winery | 27000 | 54000 | 0 | 0 | 6000 | 4500 | 91500
Coho Vineyard & Winery | 16200 | 10800 | 13500 | 9000 | 0 | 5400 | 54900
Contoso, Ltd. | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 25500
Contoso Pharmaceuticals | 7200 | 12000 | 3000 | 2000 | 0 | 1200 | 25400
Consolidated Messenger | 6480 | 2160 | 16200 | 0 | 0 | 1080 | 25920
Fabrikam, Inc. | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 25500
Fourth Coffee | 8640 | 17280 | 0 | 0 | 1920 | 1440 | 29280
Graphic Design Institute | 11520 | 7680 | 0 | 16000 | 0 | 1920 | 37120
Humongous Insurance | 19800 | 33000 | 8250 | 5500 | 0 | 3300 | 69850
Litware, Inc. | 12600 | 8400 | 0 | 17500 | 0 | 2100 | 40600
Lucerne Publishing | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 28800
Margie's Travel | 7920 | 13200 | 3300 | 2200 | 0 | 1320 | 27940
Northwind Traders | 21600 | 14400 | 18000 | 12000 | 0 | 7200 | 73200
Proseware, Inc. | 18900 | 37800 | 0 | 0 | 4200 | 3150 | 64050
School of Fine Art | 6480 | 10800 | 2700 | 1800 | 0 | 1080 | 22860
TOTAL Cost | 272340 | 319320 | 123450 | 106000 | 49320 | 53490 | 923920
TOTAL Hours | 1513 | 2661 | 823 | 1060 | 616.5 | 891.5 | 7565

## Actual Totals
[Company Name]
Event Management Project Tracker
Company Confidential
Project name | Account manager | Project manager | Strategy specialist | Design specialist | Event staff | Administration staff | Total
A. Datum Corporation | 7920 | 2640 | 19800 | 0 | 0 | 1320 | 31680
Adventure Works | 14040 | 23400 | 5850 | 3900 | 0 | 2340 | 49530
Alpine Ski House | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 58000
Baldwin Museum of Science | 5220 | 10440 | 0 | 0 | 1160 | 870 | 17690
Blue Yonder Airlines | 9180 | 3060 | 0 | 0 | 12240 | 1530 | 26010
City Power & Light | 11160 | 7440 | 9300 | 6200 | 0 | 3720 | 37820
Coho Vineyard | 18360 | 30600 | 7650 | 5100 | 0 | 3060 | 64770
Coho Winery | 28440 | 56880 | 0 | 0 | 6320 | 4740 | 96380
Coho Vineyard & Winery | 15480 | 10320 | 12900 | 8600 | 0 | 5160 | 52460
Contoso, Ltd. | 8460 | 2820 | 0 | 0 | 11280 | 1410 | 23970
Contoso Pharmaceuticals | 8460 | 14100 | 3525 | 2350 | 0 | 1410 | 29845
Consolidated Messenger | 6840 | 2280 | 17100 | 0 | 0 | 1140 | 27360
Fabrikam, Inc. | 8280 | 2760 | 0 | 0 | 11040 | 1380 | 23460
Fourth Coffee | 8100 | 16200 | 0 | 0 | 1800 | 1350 | 27450
Graphic Design Institute | 10980 | 7320 | 0 | 15250 | 0 | 1830 | 35380
Humongous Insurance | 20340 | 33900 | 8475 | 5650 | 0 | 3390 | 71755
Litware, Inc. | 12600 | 8400 | 0 | 17500 | 0 | 2100 | 40600
Lucerne Publishing | 7380 | 2460 | 18450 | 0 | 0 | 1230 | 29520
Margie's Travel | 8280 | 13800 | 3450 | 2300 | 0 | 1380 | 29210
Northwind Traders | 20160 | 13440 | 16800 | 11200 | 0 | 6720 | 68320
Proseware, Inc. | 19440 | 38880 | 0 | 0 | 4320 | 3240 | 65880
School of Fine Art | 6840 | 11400 | 2850 | 1900 | 0 | 1140 | 24130
TOTAL Cost | 273960 | 324540 | 126150 | 104950 | 48160 | 53460 | 931220
TOTAL Hours | 1522 | 2704.5 | 841 | 1049.5 | 602 | 891 | 7610