## Project Input
<Company Name>
Project Planning for Law Firms
Company Confidential
Instructions: Enter values in the white and yellow cells only.
Project Name | Project Type | Estimated Start | Estimated Finish | Estimated Work (in Hours) | Duration (in Days)
A. Datum Corporation | Business Incorporation | 2004-01-04 | 2004-03-04 | 200 | 60
Adventure Works | Business Acquisition | 2004-01-20 | 2004-02-21 | 400 | 31
Alpine Ski House | Product Liability Defense | 2004-02-06 | 2004-04-16 | 500 | 70
Baldwin Museum of Science | Patent Application | 2004-02-24 | 2004-04-25 | 150 | 61
Blue Yonder Airlines | Employee Lawsuit | 2004-03-08 | 2004-03-18 | 250 | 10
City Power & Light | Bankruptcy | 2004-03-19 | 2004-04-29 | 300 | 40
Coho Vineyard | Business Incorporation | 2004-04-10 | 2004-04-20 | 500 | 10
Coho Winery | Product Liability Defense | 2004-04-18 | 2004-05-12 | 750 | 24
Coho Vineyard & Winery | Patent Application | 2004-05-12 | 2004-06-22 | 450 | 40
Contoso, Ltd. | Bankruptcy | 2004-05-23 | 2004-07-21 | 250 | 58
Contoso Pharmaceuticals | Business Acquisition | 2004-06-14 | 2004-08-12 | 200 | 58
Consolidated Messenger | Bankruptcy | 2004-06-30 | 2004-08-30 | 180 | 60
Fabrikam, Inc. | Patent Application | 2004-01-16 | 2004-08-15 | 250 | 209
Fourth Coffee | Product Liability Defense | 2004-07-17 | 2004-09-01 | 240 | 44
Graphic Design Institute | Patent Application | 2004-07-25 | 2004-09-30 | 320 | 65
Humongous Insurance | Business Acquisition | 2004-08-01 | 2004-10-01 | 550 | 60
Litware, Inc. | Bankruptcy | 2004-08-20 | 2004-10-02 | 350 | 42
Lucerne Publishing | Business Incorporation | 2004-09-02 | 2004-11-12 | 200 | 70
Margie's Travel | Employee Lawsuit | 2004-09-12 | 2004-11-25 | 220 | 73
Northwind Traders | Bankruptcy | 2004-10-12 | 2004-12-20 | 600 | 68
Proseware, Inc. | Patent Application | 2004-10-24 | 2004-12-14 | 525 | 50
School of Fine Art | Employee Lawsuit | 2004-11-04 | 2004-11-24 | 180 | 20
TOTAL |  |  |  | 7565

## Project Parameters
<Company Name>
Project Planning for Law Firms
Company Confidential
Instructions: Enter values in the white and yellow cells only. Make sure that totals add up to 100%.
Project Type | General Partner | Business Lawyer | Defense Litigator | Intellectual Property Lawyer | Bankruptcy Lawyer | Administration Staff | Total
Business Incorporation | 10% | 40% | 0% | 0% | 0% | 50% | 100%
Business Acquisition | 10% | 40% | 0% | 10% | 0% | 40% | 100%
Product Liability Defense | 20% | 0% | 50% | 0% | 0% | 30% | 100%
Patent Application | 10% | 0% | 0% | 60% | 0% | 30% | 100%
Employee Lawsuit | 20% | 10% | 40% | 0% | 0% | 30% | 100%
Bankruptcy | 10% | 20% | 0% | 0% | 40% | 30% | 100%
Blended Rates | 350 | 250 | 300 | 275 | 225 | 125

## Calculations
<Company Name>
Project Planning for Law Firms
Company Confidential
Project Name | General Partner | Business Lawyer | Defense Litigator | Intellectual Property Lawyer | Bankruptcy Lawyer | Administration Staff | Total
A. Datum Corporation | 7000 | 20000 | 0 | 0 | 0 | 12500 | 39500
Adventure Works | 14000 | 40000 | 0 | 11000 | 0 | 20000 | 85000
Alpine Ski House | 35000 | 0 | 75000 | 0 | 0 | 18750 | 128750
Baldwin Museum of Science | 5250 | 0 | 0 | 24750 | 0 | 5625 | 35625
Blue Yonder Airlines | 17500 | 6250 | 30000 | 0 | 0 | 9375 | 63125
City Power & Light | 10500 | 15000 | 0 | 0 | 27000 | 11250 | 63750
Coho Vineyard | 17500 | 50000 | 0 | 0 | 0 | 31250 | 98750
Coho Winery | 52500 | 0 | 112500 | 0 | 0 | 28125 | 193125
Coho Vineyard & Winery | 15750 | 0 | 0 | 74250 | 0 | 16875 | 106875
Contoso, Ltd. | 8750 | 12500 | 0 | 0 | 22500 | 9375 | 53125
Contoso Pharmaceuticals | 7000 | 20000 | 0 | 5500 | 0 | 10000 | 42500
Consolidated Messenger | 6300 | 9000 | 0 | 0 | 16200 | 6750 | 38250
Fabrikam, Inc. | 8750 | 0 | 0 | 41250 | 0 | 9375 | 59375
Fourth Coffee | 16800 | 0 | 36000 | 0 | 0 | 9000 | 61800
Graphic Design Institute | 11200 | 0 | 0 | 52800 | 0 | 12000 | 76000
Humongous Insurance | 19250 | 55000 | 0 | 15125 | 0 | 27500 | 116875
Litware, Inc. | 12250 | 17500 | 0 | 0 | 31500 | 13125 | 74375
Lucerne Publishing | 7000 | 20000 | 0 | 0 | 0 | 12500 | 39500
Margie's Travel | 15400 | 5500 | 26400 | 0 | 0 | 8250 | 55550
Northwind Traders | 21000 | 30000 | 0 | 0 | 54000 | 22500 | 127500
Proseware, Inc. | 18375 | 0 | 0 | 86625 | 0 | 19687.5 | 124687.5
School of Fine Art | 12600 | 4500 | 21600 | 0 | 0 | 6750 | 45450
TOTAL Cost | 339675 | 305250 | 301500 | 311300 | 151200 | 320562.5 | 1729487.5
TOTAL Hours | 970.5 | 1221 | 1005 | 1132 | 672 | 2564.5 | 7565