START-UP PROJECT PLAN

[INSERT NAME OF THE BUSINESS/COMPANY]

[INSERT THE COMPLETE BUSINESS/COMPANY ADDRESS]

[INSERT THE BUSINESS/COMPANY CONTACT NUMBERS]

[INSERT THE BUSINESS/COMPANY EMAIL ADDRESS]

[INSERT THE BUSINESS/COMPANY WEBSITE ADDRESS]

DEPARTMENT:

[SEO TEAM]

[INSERT DATE]

PREPARED BY:

[INSERT FULL NAME/S OF THE

PEOPLE WHO PREPARED THIS PLAN]

PROJECT NAME:

[SEO INTEGRATION IN ALL MARKETING CONTENT]

PROJECT SPONSOR:

[MARKETING TEAM]

Department Strategic Goals:

1. Establish a seamless flow of responsibilities during the integration of the [SEO] as a new way of marketing the business.

2. Integrate [SEO] in a manner that does not heavily disrupt existing processes, thereby maintaining team efficiency.

Project Description:

The marketing team sees the need to integrate [SEO] to improve its contents' ranking on web searches and increase customer visits to the company web pages. The team will use tons of [SEO] data to connect its marketing content to the right customers. The team makes sure that this initiative would seamlessly flow into existing work processes.

Project Objectives:

1. Increase [Search Engine Results Pages] (SERP) ranking on all contents

2. Increase customer visits to company web page and content to [75%] by end of the year

Organizational Chart:

The marketing team is composed of nine people. Shown below is their organizational chart:

Melissa Stone, Marketing Manager

SEO

Howard McKinley

Shawn Williams

Social Media

Ernest Roberts

Frances Jones

Writer/Editor

Lois Lewis

Jose Harmon

Sales and Marketing

Danny Orton

Debra Paige

Marketing Team

Project Activities:

| Activities | Owner | Target Completion Date | Updates |
| --- | --- | --- | --- |
| 1. Gather relevant data to identify market demand | Debra Paige | End of the second quarter 2019 | - Debra has started interpreting the collected data |
| 2. Optimize contents according to Debra’s report | Howard McKinley | Start of the third quarter 2019 | - Howard will share his SEO insights to content writers |

Process Map

The following is the SEO integration workflow process:

SEO Strategist Creates a Topic

Content Writer Provides the Content

Production Manager Uploads to Content Management System

SEO Strategist Reviews the Product

Graphic Designer Creates the Image

Reviewed and Revised by the Editor

Reviewed and Revised by Senior Designer

Marketing Manager Approves the Product

Design Team Runs User Test

Production Manager Publishes the Output

Project Budget Proposal:

| Item Description | No. of Items | Cost Per Item | Proposed Budget in USD | Actual Cost |
| --- | --- | --- | --- | --- |
| Data Analytics Software | 1 | $3,000.00 | $1,500.00 | $3,000.00 |
| Server | 9 | $660.00 | $5,000.00 | $5,940.00 |
| TOTAL |  |  | $6,500.00 | $8,940.00 |

Operational Plan Review:

Key Initiatives

1. Identify market demands

2. Train content writers on search engine optimization

Current Issues

1. The proposed budget is lesser than the actual cost of the project

2. SEO Strategist does not have enough time to train content writers

Action Items

1. Propose a new budget for the project

2. Create a digital reading material for writers

Accomplishments

1. A new budget proposal is made

2. Data collection is finished

Legend:

Project/action item is progressing on schedule.

Project/action item is delayed or lacks a requirement.

Project/action item is stopped. The project may not be completed.

Performance Indicator:

| Goals/Objectives | Outcome Description |
| --- | --- |
| 1. Increase Search Engine Results Pages (SERP) ranking on all contents | The new content marketing workflow will help increase the effectiveness of each content and will give it a higher ranking on popular search engines. |
| 2. Increase customer visits to company web page and content to 75% by end of the year | The integration of SEO into the team’s work process will help increase the company website’s visibility thereby increasing customer visits |