## Sheet1
Construction Contract Payment Schedule
Contractor: |  |  |  | Contractee:
[ABC Construction Company] |  |  |  | [John]
[806 Smith Avenue Duarte, CA 91010] |  |  |  | [10 High Point Dr. Ames, IA 50010]
[2025550114] |  |  |  | [2025550180]
Total Contract Amount |  | 300000
Amount Breakup | Description |  | Completion Date | Completed On | Payment Claimed | Payment Made | Payment Date
10% | Foundation |  | 2019-03-27 | 2019-03-27 | 30000 | 30000 | 2019-03-30
5% | Earthworks |  | 2019-04-01 | 2019-04-01 | 15000 | 15000 | 2019-04-04
8% | Concrete Frame Work |  | 2019-04-03 | 2019-04-03 | 24000 | 24000 | 2019-04-06
10% | Brick wall |  | 2019-04-09 | 2019-04-09 | 30000 | 30000 | 2019-04-12
7% | Roofing |  | 2019-04-10 | 2019-04-10 | 21000 | 21000 | 2019-04-12
5% | Electrical Work |  | 2019-04-18 | 2019-04-20 | 15000 | 14823 | 2019-04-25
6% | Plumbing |  | 2019-04-25 | 2019-04-25 | 18000 | 18000 | 2019-04-28
10% | Wood Work |  | 28-04-201 | 2019-04-29 | 30000 | 29750 | 2019-04-30
4% | Water Pipe, Drainage |  | 2019-04-30 | 2019-05-01 | 12000 | 11829 | 2019-05-01
15% | Municipal permits |  | 2019-03-20 | 2019-03-20 | 45000 | 45000 | 2019-03-25
20% | Transfer of ownership |  | 2019-03-23 | 2019-03-23 | 60000 | 60000 | 2019-03-25
Total |  |  |  |  | 300000 | 299402
Note:
1. Payment can be claimed upon the individual task completion.
2. If the task is not completed on time or defects found in it then payment will be processed after deducting 1%-5% of the claim amount.